## to be proposed
|  | UAT SCHEDULE ACTIVITY (DRAFT) |  |  | 103
[6 empty] | UAT | [5 empty] | Deployment |  | August |  |  |  | September | [19 empty] | October
[14 empty] | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed
BLOCK | CRITERIA | NO | CODE | FUNCTION | DESCRIPTION | RELATED PIC | DAYS | AGIT Team | Scenario | Execution |  | Function |  | 28 | 29 | 30 | 31 | 1 | 4 | 5 | 6 | 7 | 8 | 11 | 12 | 13 | 14 | 15 | 18 | 19 | 20 | 21 | 22 | 25 | 26 | 27 | 29 | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31
|  | NO | CODE | FUNCTION | DESCRIPTION |  |  |  | Numbers | Start Date | Status | Start Date | Status
ORDER TAKING | PROCESS | 1 | OTP-001 | Order Type 1 & 2 | Order Taking Type 1 by entry & upload | AAR, JFS, OAS | 6 | B | 90 | 2023-09-08
|  | 2 | OTP-003 | Order Type 3 & C | Order Taking Type 3 by entry & upload | AAR, JFS, OAS | 6 | B |  | 2023-09-08
|  | 3 | OTP-007 | Order Optional Source | VOR Order taking to optional source | AAR, JFS, OAS | 6 | B |  | 2023-09-08
|  | 4 | OTP-008 | Order for Manual Handling Submission | Order taking for unregistered PN (R1) & tapping items | AAR, JFS, RS | 6 | B |  | 2023-09-08
|  | 5 | OTP-009 | Order Manual Processing | Order manual processing in TAM | AAR, JFS, RS, ADP | 6 | B |  | 2023-09-08
|  | 6 | OTL-001 | Order Log | Order Log | AAR, JFS, OAS, RS | 2 | B | 12 | 2023-09-08
|  | 7 | OTS-003 | Order sent to GT CD | Order sent to GT by night batch (Connect Direct) | AAR, JFS, OAS | 2 | B |  | 2023-09-08
|  | 8 | OTS-004 | Order Monitoring & Maintenance | Order Monitoring & Maintenance before GT | AAR, JFS, OAS | 2 | B | 4 | 2023-09-15
| MASTER | 9 | OTM-001 | Transport Code Master | Transportation Code Convertion | AAR, JFS, OAS | 2 | B | 23 | 2023-08-31
|  | 10 | OTM-002 | Order Lot Qty Master | Direct delivery Recognation or Lot Qty validation | AAR, JFS, OAS | 2 | B |  | 2023-08-31
|  | 11 | OTM-003 | Lexus Customer Master | Lexus customer Recognation | AAR, JFS, OAS | 2 | B |  | 2023-08-31
|  | 12 | OTM-004 | Working Calendar Master | Online offline screen assignment base on date | AAR, JFS, OAS | 2 | B |  | 2023-08-31
|  | 13 | OTM-005 | Remarks Master Maint. | Order Remark Mapping | AAR, JFS, OAS | 2 | B |  | 2023-08-31
|  | 14 | OTM-006 | Set Upload Off | Online offline screen assignment base on time | AAR, JFS, OAS | 2 | B |  | 2023-08-31
|  | 15 | OTM-009 | TPOS Customer Order Grouping Master | Validate ordered PN based on customer grouping | AAR, JFS, OAS | 2 | B |  | 2023-08-31
|  | 16 | OTM-010 | TPOS Order Monitoring Master | Order Monitoring criteria | AAR, JFS, OAS | 2 | B |  | 2023-08-31
|  | 17 | OTM-011 | TPOS Destination Convertion Master | Customer code mapping for flexible destination order | AAR, JFS, OAS | 2 | B |  | 2023-08-31
ORDER TAKING | PABLO | 18 | OTP-006 | UPLOAD Order Type C (Campaign Code) | Order Taking Type C (PABLO) by Upload | AAR, MK | 5 | B |  | 2023-09-08
| TIRE & MERCHANDIZE | 19 | OTP-005 | Order Type T | Order Taking Type T by entry & upload | AAR, PL | 5 | B |  | 2023-09-08
| LOG & OTH | 20 | OTL-002 | Order Log - Tire | Order Log - Tire | AAR, PL | 2 | B |  | 2023-09-08
| MASTER | 21 | OTM-007 | Mapping Branch - Supplier | Tire business mapping customer code to supplier | AAR, PL | 2 | B |  | 2023-08-31
INQUIRY | INQUIRY | 22 | INQ-002 | Stock Inquiry - Tire | Tire stock inquiry base on customer | AAR, PL | 3 | A | 92 | 2023-09-19 | bar: September Tue 19 to September Fri 22
|  | 23 | INQ-001 | Part Master Inquiry | Part master inquiry for customer purpose | AAR, JFS, OAS | 3 | A |  | 2023-09-19 | bar: September Tue 19 to September Fri 22
|  | 24 | INQ-003 | General Part Master | Part master inquiry for internal TAM purpose | AAR, JFS, OAS | 2 | A |  | 2023-09-19 | bar: September Tue 19 to September Fri 22
|  | 25 | INQ-004 | BO ETD Inquiry | BO ETD information Inquiry | AAR, JFS, OAS | 2 | A |  | 2023-09-19 | bar: September Tue 19 to September Fri 22
|  | 26 | INQ-005 | Order Status Inquiry | Order Status information inquiry | AAR, JFS, OAS | 3 | A |  | 2023-09-19 | bar: September Tue 19 to September Fri 22
|  | 27 | INQ-006 | Shipment Detail Inquiry | Shipment detail information inqury | AAR, JFS, OAS | 2 | A |  | 2023-09-19 | bar: September Tue 19 to September Fri 22
|  | 28 | INQ-007 | BO Detail Inquiry | BO Detail information inquiry | AAR, JFS, OAS | 2 | A |  | 2023-09-19 | bar: September Tue 19 to September Fri 22
|  | 29 | INQ-008 | POSS Inquiry | POSS information inquiry | AAR, JFS, OAS | 2 | A |  | 2023-09-19 | bar: September Tue 19 to September Fri 22
|  | 30 | INQ-009 | Pending Detail Inquiry | Pending Detail information inquiry | AAR, JFS, OAS | 2 | A |  | 2023-09-19 | bar: September Tue 19 to September Fri 22
|  | 31 | INQ-010 | Order Status Inquiry - Tire | Tire Order Status inquiry | AAR, PL | 3 | A |  | 2023-09-19 | bar: September Tue 19 to September Fri 22
|  | 32 | INQ-011 | Order Status Inquiry Campaign (Stacking) | Order Status Inquiry for Campaign (Stacking) | AAR, MK | 2 | A |  | 2023-09-19 | bar: September Tue 19 to September Fri 22
|  | 33 | INQ-012 | Order Status Inquiry Manual Handling | Order Status Inquiry for Manual handling items | AAR, JFS, OAS | 3 | A |  | 2023-09-19 | bar: September Tue 19 to September Fri 22
| MASTER | 34 | INM-001 | TPOS Stock Assignment Master | Master for fixed stock assignment | AAR, JFS, OAS | 2 | A | 12 | 2023-09-06 | bar: September Wed 6 to September Thu 7
|  | 35 | INM-002 | TPOS Production Leadtime Master | Master for PN production LT information | AAR, JFS, OAS | 2 | A |  | 2023-09-06 | bar: September Wed 6 to September Thu 7
CLAIM | PROCESS | 36 | CLP-001 | Claim Registration PC | Part claim registration menu | AAR, MM, LST | 3 | C | 137 | 2023-09-25 | bar: September Mon 25 to October Mon 1
|  | 37 | CLP-002 | Claim Registration RPP | RPP claim registration menu | AAR, MM, LST | 3 | C |  | 2023-09-25 | bar: September Mon 25 to October Mon 1
|  | 38 | CLP-003 | Re-claim Registration | Re-claim registration for 1st rejected claim | AAR, MM, LST | 3 | C |  | 2023-09-25 | bar: September Mon 25 to October Mon 1
|  | 39 | CLP-005 | Claim Inquiry | Claim Data inquiry | AAR, MM, LST | 2 | C |  | 2023-09-25 | bar: September Mon 25 to October Mon 1
|  | 40 | CLP-006 | Manual Claim Judgement | Claim judgment by TAM PIC | AAR, MM, LST, SR, ADP, BI | 3 | C |  | 2023-09-25 | bar: September Mon 25 to October Mon 1
|  | 41 | CLP-007 | TAM Claim Approval | Claim final judgment by TAM Supervisor | AAR, MM | 3 | C |  | 2023-09-25 | bar: September Mon 25 to October Mon 1
|  | 42 | CLP-008 | Re-Judgement Claim | Re-Judgement Claim (for judgment revision) | AAR, MM | 3 | C |  | 2023-09-25 | bar: September Mon 25 to October Mon 1
|  | 43 | CLP-009 | Physical Part return monitoring | Physical Part return monitoring from dealer to TAM | AAR, MM, SR, BI | 5 | C |  | 2023-09-25 | bar: September Mon 25 to October Mon 1
| MASTER | 44 | CLM-001 | Claim Department Code Master | Mapping claim code to authorized dept. | AAR, MM | 2 | C | 12 | 2023-09-06 | bar: September Wed 6 to September Thu 7
|  | 45 | CLM-002 | Claim Code | Claim code master & mapping | AAR, MM | 2 | C |  | 2023-09-06 | bar: September Wed 6 to September Thu 7
|  | 46 | CLM-004 | Judgement Code | Claim judgment code master | AAR, MM | 2 | C |  | 2023-09-06 | bar: September Wed 6 to September Thu 7
|  | 47 | CLM-005 | Claim Judgment Leadtime Master | Claim judgment LT master for auto-judgment | AAR, MM | 2 | C |  | 2023-09-06 | bar: September Wed 6 to September Thu 7
DATA DOWNLOAD |  | 48 | DDW-001 | Proforma Invoice Data Download | Download invoice data | AAR, JFS, OAS | 3 | B | 49 | 2023-10-02
|  | 49 | DDW-002 | POSS Data Download | Download POSS data | AAR, JFS, OAS | 3 | B |  | 2023-10-02
|  | 50 | DDW-003 | BO Data Download | Download BO data | AAR, JFS, OAS | 3 | B |  | 2023-10-02
|  | 51 | DDW-004 | Packing List Data Download | Download Packing list data | AAR, JFS, OAS | 3 | B |  | 2023-10-02
|  | 52 | DDW-005 | Debit Advice Data Download | Download Debit advice data | AAR, JFS, OAS | 3 | B |  | 2023-10-02
|  | 53 | DDW-006 | Credit Advice Data Download | Download Credit advice data | AAR, JFS, OAS | 3 | B |  | 2023-10-02
|  | 54 | DDW-007 | Pending Data Download | Download Pending data | AAR, JFS, OAS | 3 | B |  | 2023-10-02
|  | 55 | DDW-008 | Reject Data Download | Download Reject data | AAR, JFS, OAS | 3 | B |  | 2023-10-02
BO ETD | PROCESS | 56 | BOP-001 | BO ETD Update | BO ETD Update by night batch | AAR, JFS, OAS, AAS | 6 | C | 9 | 2023-10-05 | bar: October Fri 5 to October Fri 12
|  | 57 | BOP-002 | BO ETD TPOS Flagging | BO ETD TPOS Flagging process | AAR, JFS, OAS | 6 | C |  | 2023-10-05 | bar: October Fri 5 to October Fri 12
| REPORT | 58 | BOR-001 | BO ETD Accuracy Screen | BO ETD Accuracy Report Screen | AAR, JFS, OAS | 6 | C |  | 2023-10-05 | bar: October Fri 5 to October Fri 12
|  | 59 | BOR-002 | BO ETD Fillrate Report | BO ETD Fillrate Report screen | AAR, JFS, OAS | 6 | C |  | 2023-10-05 | bar: October Fri 5 to October Fri 12
| MASTER | 60 | BOM-001 | ETD Email Notification | ETD Email Notification for ETD change information | AAR, JFS, OAS | 2 | C |  | 2023-09-15 | bar: September Fri 15 to September Mon 18
|  | 61 | BOM-002 | ETD Email Content | ETD Email Content (template for notification) | AAR, JFS, OAS | 2 | C |  | 2023-09-15 | bar: September Fri 15 to September Mon 18
LOGCOM | PROCESS | 62 | LCP-001 | Post Order Inquiry | Post Order Inquiry from dealer to TAM | AAR, OAS | 6 | C | 36 | 2023-10-15 | bar: October Fri 12 to October Fri 19
|  | 63 | LCP-002 | Post Order Escalation | Post Order Escalation | AAR, OAS, RS, AP | 6 | C |  | 2023-10-15 | bar: October Fri 12 to October Fri 19
|  | 64 | LCP-003 | Post Order Answer | Post Order Answer | AAR, OAS, RS, AP | 6 | C |  | 2023-10-15 | bar: October Fri 12 to October Fri 19
|  | 65 | LCP-004 | Post Order Auto-close Ticket | Post Order Auto-close | AAR, OAS | 2 | C |  | 2023-10-15 | bar: October Fri 12 to October Fri 19
|  | 66 | LCP-005 | Pre-order Inquiry | Pre-order Inquiry from customer to TAM | AAR, OAS | 6 | C |  | 2023-10-15 | bar: October Fri 12 to October Fri 19
|  | 67 | LCP-006 | Pre-order Answer | Pre-order Answer | AAR, OAS, ADP | 6 | C |  | 2023-10-15 | bar: October Fri 12 to October Fri 19
|  | 68 | LCP-007 | Ticket Inquiry | Ticket inquiry menu | AAR, OAS, AP, ADP | 2 | C |  | 2023-10-15 | bar: October Fri 12 to October Fri 19
| REPORT | 69 | LCR-001 | Dashboard Monitoring & Reporting | Ticket dahsboard & reporting screen | AAR, OAS, AP, ADP | 6 | C | 5 | 2023-10-15 | bar: October Fri 12 to October Fri 19
| MASTER | 70 | LCM-001 | LogCom Part Master | Update LogCom Part master by night batch | AAR, OAS | 2 | B | 8 | 2023-09-06 | bar: September Wed 6 to September Fri 8
|  | 71 | LCM-003 | Pre-Order Inquiry Master | Pre-Order Inquiry Master | AAR, OAS | 2 | B |  | 2023-09-06 | bar: September Wed 6 to September Fri 8
|  | 72 | LCM-004 | ETD Lead-time Master | BO ETD Lead-time Master | AAR, OAS | 2 | B |  | 2023-09-06 | bar: September Wed 6 to September Fri 8
|  | 73 | LCM-005 | ETD answer reference table | BO ETD answer reference table | AAR, OAS | 3 | B |  | 2023-09-06 | bar: September Wed 6 to September Fri 8
|  | 74 | LCM-006 | LogCom flag master | LogCom reason flag master | AAR, OAS | 2 | B |  | 2023-09-06 | bar: September Wed 6 to September Fri 8
PART RETURN | PROCESS | 75 | PRP-001 | Return Data Maintenance | For maintain mis-return data processed | AAR, MM, LST | 3 | A | 10 | 2023-10-02 | bar: October Tue 2 to October Thu 4
DIRECT DELIVERY | PROCESS | 76 | DDP-001 | Case No Registration | Case No Registration for DD ASN | AAR, SUP | 2 | B | 9 | 2023-10-02
|  | 77 | DDP-002 | Manual Invoice Creation | Direct Deliv. Manual DN data Creation for Invoicing | AAR, SUP | 3 | B |  | 2023-10-02
DELIVERY MONITORING | PROCESS | 78 | DMP-001 | TAM Shipment ATA | TAM Delivery actual arrival manual input | AAR, OAS, SR | 3 | B | 9 | 2023-10-02
ADMIN MENU | MASTER | 79 | ADM-001 | Role Maintenance | TPOS Role Maintenance | AAR, JFS, OAS | 2 | A | 21 | 2023-08-31 | bar: August Thu 31 to September Mon 4
|  | 80 | ADM-002 | Destination Master | TPOS Destination code mapping Master | AAR, JFS, OAS | 2 | A |  | 2023-08-31 | bar: August Thu 31 to September Mon 4
|  | 81 | ADM-003 | User Maintenance | TPOS User Maintenance | AAR, JFS, OAS | 2 | A |  | 2023-08-31 | bar: August Thu 31 to September Mon 4
|  | 82 | ADM-004 | Archiving | Data Archiving Management | AAR, JFS, OAS | 5 | A |  | 2023-10-18 | bar: October Fri 19 to October Fri 26
OTHERS | PROCESS | 83 | XOT-001 | Log Monitoring | Log Monitoring for all TPOS transaction | AAR, JFS, OAS | 2 | C | 13 | 2023-09-01 | bar: September Fri 1 to September Tue 5
|  | 84 | XOT-002 | Help Book Setting | Upload helpbook data | AAR, JFS, OAS | 2 | C |  | 2023-09-01 | bar: September Fri 1 to September Tue 5
|  | 85 | XOT-003 | Upload Pending Detail | Upload Pending Detail data | AAR, JFS, OAS | 2 | C |  | 2023-09-01 | bar: September Fri 1 to September Tue 5
|  | 86 | XOT-004 | Help Book Download | Help Book Download for user | AAR, JFS, OAS | 2 | C |  | 2023-09-01 | bar: September Fri 1 to September Tue 5
|  | 87 | XOT-005 | Realtime Announcement | Realtime Announcement for TPOS user | AAR, JFS, OAS | 3 | C |  | 2023-09-01 | bar: September Fri 1 to September Tue 5
|  | 88 | XOM-002 | R/A Master Maintenance | R/A Code Master Maintenance | AAR, JFS, OAS | 2 | C | 6 | 2023-09-01 | bar: September Fri 1 to September Tue 5
|  | 89 | XOM-003 | System Master Maintenance | System Master Maintenance | AAR, JFS, OAS | 2 | C |  | 2023-09-01 | bar: September Fri 1 to September Tue 5
DIRECT DATA | DB to DB | 90 | DTD-001 | PO Response | DB to DB Process for DMD-PO Response | AAR, JFS, OAS | 2 | C | 12 | 2023-10-19 | bar: October Fri 19 to October Tue 23
|  | 91 | DTD-002 | ETD Inquiry Request | DB to DB Process for DMD-ETD Inquiry Request | AAR, JFS, OAS | 2 | C |  | 2023-10-19 | bar: October Fri 19 to October Tue 23
|  | 92 | DTD-003 | Debit Advice Data | DB to DB Process for DMD-Debit Advice Data | AAR, JFS, OAS | 2 | C |  | 2023-10-19 | bar: October Fri 19 to October Tue 23
|  | 93 | DTD-004 | Credit Advice Data | DB to DB Process for DMD-Credit Advice Data | AAR, JFS, OAS | 2 | C |  | 2023-10-19 | bar: October Fri 19 to October Tue 23
|  | 94 | DTD-005 | Goods Receipt & Packing List Inquiry | DB to DB Process for DMD-Goods Receipt & Packing List Inquiry | AAR, JFS, OAS | 2 | C |  | 2023-10-19 | bar: October Fri 19 to October Tue 23
|  | 95 | DTD-006 | Invoice | DB to DB Process for DMD-Invoice | AAR, JFS, OAS | 2 | C |  | 2023-10-19 | bar: October Fri 19 to October Tue 23
|  | 96 | DTD-007 | Parts Claim | DB to DB Process for DMD-Parts Claim | AAR, JFS, OAS | 2 | C |  | 2023-10-19 | bar: October Fri 19 to October Tue 23
|  | 97 | DTD-008 | Purchase Order Response/Result | DB to DB Process for DMD-Purchase Order Response/Result | AAR, JFS, OAS | 2 | C |  | 2023-10-19 | bar: October Fri 19 to October Tue 23
|  | 98 | DTD-009 | RPP | DB to DB Process for DMD-RPP | AAR, JFS, OAS | 2 | C |  | 2023-10-19 | bar: October Fri 19 to October Tue 23
|  | 99 | COM-001 | Global Function Insert Log | General Setting for-Global Function Insert Log | AAR, JFS, OAS | 2 | A | 7 | 2023-10-24 | bar: October Wed 24 to October Fri 26
|  | 100 | COM-002 | Log SuccesscError All Module | General Setting for-Log SuccesscError All Module | AAR, JFS, OAS | 2 | A |  | 2023-10-24 | bar: October Wed 24 to October Fri 26
|  | 101 | COM-003 | Approval Engine | General Setting for-Approval Engine | AAR, JFS, OAS | 2 | A |  | 2023-10-24 | bar: October Wed 24 to October Fri 26
|  | 102 | COM-004 | My Pending Approval | General Setting for-My Pending Approval | AAR, JFS, OAS | 2 | A |  | 2023-10-24 | bar: October Wed 24 to October Fri 26
|  | 103 | COM-005 | Login User Non HO & TAM Passport | General Setting for-Login User Non HO & TAM Passport | AAR, JFS, OAS | 2 | A |  | 2023-10-24 | bar: October Wed 24 to October Fri 26
|  | 103 |  |  |  |  | 302 |  | 576
PIC:
Notes: | ISTD | - AAR | = Ali Akbar , SPLD - SM |  | Aug. 31 - Oct. 26, 2023
| SPLD - SM | - JFS | = Juliandris FS , SPLD - SM |  | Aug. 31 - Sep. 22, 2023; Oct. 2-12, 2023; Oct. 19-26, 2023
|  | - OAS | = Osel Aditya S. , SPLD - SM |  | Aug. 31 - Sep. 22, 2023; Oct. 2-26, 2023
|  | - MM | = Manama M. , SPLD - SM |  | Sep. 6-7, 2023; Sep.25 - Oct. 4, 2023
|  | - RS | = Riang Sunandar , SPLD - SM |  | Sep. 8-18, 2023; Oct. 12-19, 2023
|  | - LST | = Listiowati , SPLD - SM |  | Sep.25 - Oct. 4, 2023
|  | - SR | = Sopian Riady , SPLD - SM |  | Sep.25 - Oct. 4, 2023
|  | - SUP | = Supriyadi , SPLD - SM |  | Oct. 2-4, 2023
|  | - AP | = Anton P. , SPLD - SM |  | Oct. 12-19, 2023
|  | - BI | = Bastaman Irfansuri , SPLD - WRH |  | Sep.25 - Oct. 1, 2023
|  | - AAS | = Aas Astri A. , SPLD - IM |  | Oct. 5-12, 2023
|  | - ADP | = Adi Permadi , SPLD - SPPM |  | Sep. 8-18, 2023; Sep. 25-Oct. 1 ,2023; Oct. 12-18, 2023
|  | - PL | = Pradipta L. , ASBD |  | Aug. 31 - Sep. 4, 2023; Sep. 8-22, 2023
|  | - MK | = Martha K. , ASBD |  | Sep. 8-22, 2023